## Skill Matrix
Rnai — AI Skill Catalog
17 skills across 4 categories · 1 credit = $0.01 sell · costs are estimates Q2 2026
Category | Skill | Status | Endpoint | Primary model | Fallback model | Unit | Credits / unit | Est. provider cost (USD/unit) | Sell price (USD/unit) | Margin %
Image | Generate | ✅ live | /v1/image/generate | FLUX.1-schnell (HF) | SDXL-Lightning | image | 5 | 0.003 | 0.05 | 94%
Image | Edit / Inpaint | ✅ live | /v1/image/edit | SDXL-1.0-inpainting | FLUX.1-Fill (fal) | image | 8 | 0.005 | 0.08 | 93.75%
Image | Remove BG | ✅ live | /v1/image/remove-bg | RMBG-1.4 | BiRefNet | image | 2 | 0.001 | 0.02 | 95%
Image | Upscale 4× | 🆕 plan | /v1/image/upscale | Real-ESRGAN-x4 | clarity-upscaler | image | 3 | 0.002 | 0.03 | 93.33%
Image | Style transfer | 🆕 plan | /v1/image/stylize | IP-Adapter + SDXL | Stable Cascade | image | 6 | 0.004 | 0.06 | 93.33%
Text/LLM | Chat completion | 🆕 plan | /v1/text/chat | Llama-3.1-70B (Together) | Mixtral-8x7B (OR) | 1K tok out | 2 | 0.0009 | 0.02 | 95.5%
Text/LLM | Summarize | 🆕 plan | /v1/text/summarize | Llama-3.1-8B | DistilBart-CNN | 1K tok in | 0.5 | 0.0002 | 0.005 | 96%
Text/LLM | Translate | 🆕 plan | /v1/text/translate | NLLB-200-3.3B | Llama-3-8B (zero-shot) | 1K tok in | 0.5 | 0.0002 | 0.005 | 96%
Text/LLM | Embeddings | 🆕 plan | /v1/text/embeddings | nomic-embed-text-v1.5 | bge-m3 | 1K tok | 0.05 | 2e-05 | 0.0005 | 96%
Text/LLM | Rerank | 🆕 plan | /v1/text/rerank | bge-reranker-v2-m3 | jina-reranker-v2 | request | 0.1 | 5e-05 | 0.001 | 95%
Audio | Text-to-speech | 🆕 plan | /v1/audio/tts | XTTS-v2 (Coqui) | parler-tts-mini | 100 chars | 1 | 0.0003 | 0.01 | 97%
Audio | Speech-to-text | 🆕 plan | /v1/audio/transcribe | Whisper-large-v3 | distil-whisper-v3 | minute | 3 | 0.0008 | 0.03 | 97.33%
Audio | Music generation | 🆕 plan | /v1/audio/music | MusicGen-medium | Stable-Audio-Open | 30s clip | 10 | 0.005 | 0.1 | 95%
Audio | Voice cloning | 🆕 plan | /v1/audio/clone | XTTS-v2 (clone mode) | F5-TTS | request | 8 | 0.004 | 0.08 | 95%
Video & 3D | Text-to-video | 🆕 plan | /v1/video/generate | LTX-Video (fal) | CogVideoX-2B | 5s clip | 30 | 0.018 | 0.3 | 94%
Video & 3D | Lip-sync | 🆕 plan | /v1/video/lipsync | Wav2Lip | LatentSync | request | 20 | 0.012 | 0.2 | 94%
Video & 3D | Image-to-3D | 🆕 plan | /v1/3d/from-image | TripoSR | InstantMesh | request | 15 | 0.008 | 0.15 | 94.67%
Average | [9 empty] | 95%

## Pricing
Pricing & Topup Packs
Pay-as-you-go · 1 credit = $0.01 base · packs give discount
Free quota
Free credits / month | 200 | ≈ 40 image generations · 200K LLM input tok
Reset cadence | Monthly (1st) | via cron
Eligibility | Email-verified accounts | 1 quota per device fingerprint
Hard stop when 0 | Yes | API returns 402 unless paid balance > 0
Topup packs (paid)
Pack | Price (USD) | Credits | Effective $/credit | Bonus vs base
Starter | 5 | 600 | 0.0083333 | 16.67%
Pro | 20 | 2500 | 0.008 | 20%
Scale | 100 | 13500 | 0.0074074 | 25.93%
Business | 500 | 75000 | 0.0066667 | 33.33%
Comparison vs competitors (per 1024×1024 image gen)
Provider | Price (USD) | Notes
Rnai (this plan) | 0.05 | 5 credits @ $0.01 — Pro pack lowers to $0.04
Replicate FLUX schnell (cost) | 0.003 | Direct provider cost
OpenAI DALL-E 3 standard | 0.04 | 1024×1024
Midjourney basic | 0.027 | $10 / mo / ~370 fast hours
Stability SD3 | 0.065 | API direct

## Roadmap
12-week implementation roadmap
4 phases · build sequentially · gating items must clear before next phase
Phase | Week | Workstream | Deliverable | Owner | Gating?
Phase 0 — Security | W1 | Secrets | Rotate Firebase key, HF token; clean .env.example; git filter-repo | You | YES
Phase 0 — Security | W1 | Auth | httpOnly cookie via /api/auth/session; middleware verifies token | You | YES
Phase 0 — Security | W1 | Rate limit | Upstash Redis token bucket — 60 req/min per key | You | YES
Phase 1 — Billing | W2 | Schema | users + ledgerEntries + usageLogs collections; cron reset free quota | Backend | —
Phase 1 — Billing | W2 | Credits | lib/billing/credits.ts — reserve/commit/refund (transactional) | Backend | —
Phase 1 — Billing | W3 | Pricing | lib/billing/pricing.ts table + middleware to charge existing 3 endpoints | Backend | —
Phase 1 — Billing | W3 | Stripe | Checkout + webhook for 3 topup packs; Customer Portal | Backend | —
Phase 1 — Billing | W4 | Dashboard | /dashboard/billing balance + history; usage chart | Frontend | —
Phase 1 — Billing | W4 | Observability | Sentry; request log retention 30d | DevOps | —
Phase 2 — Skills | W5 | Refactor | Provider router + skill registry; migrate 3 existing skills | Backend | YES
Phase 2 — Skills | W5 | Image+ | Add upscale + stylize | Backend | —
Phase 2 — Skills | W6-7 | Text/LLM | 5 text skills via Together / OpenRouter | Backend | —
Phase 2 — Skills | W7-8 | Audio | TTS + STT + music + clone | Backend | —
Phase 2 — Skills | W8 | Async jobs | QStash queue for >10s skills; /api/jobs/[id] | Backend | —
Phase 2 — Skills | W9 | Storage | Vercel Blob + signed URL; deprecate base64 input | Backend | —
Phase 2 — Skills | W9 | Cache | 24h cache by inputHash for idempotent skills | Backend | —
Phase 3 — Polish | W10 | Video/3D | Video gen + lipsync + image-to-3D (async) | Backend | —
Phase 3 — Polish | W11 | Playground | /playground page tests every skill from browser | Frontend | —
Phase 3 — Polish | W11 | Docs | OpenAPI spec + Mintlify docs site + cookbook | Docs | —
Phase 3 — Polish | W12 | SDK | @rnai/sdk TS client; publish npm | Backend | —
Phase 3 — Polish | W12 | Launch | Status page; PH launch; HF community post | Marketing | YES

## Financial
12-month financial projection (USD)
Conservative scenario · blue = inputs, edit to change scenario · black = formulas
Assumptions
Starting paid users (M1) | 20 | from soft launch / mailing list
Monthly user growth rate | 20% | 20% MoM realistic for indie launch
Free→Paid conversion | 5% | 5% of free users buy first pack
Free signups / paid user | 8 | for every 1 paid we gain 8 free
ARPU (paid, USD/mo) | 18 | blended pack purchase
Free user infra cost / mo | 40% | 200 free credits × $0.002
Paid user infra cost ratio | 40% | 40% of revenue = provider cost
Stripe fee | 2.9% | 2.9% + $0.30/charge — modeled as %
Fixed infra (Vercel/Upstash/etc.) | 80 | USD / month
Metric | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Total
Paid users (active) | 20 | 24 | 28.8 | 34.56 | 41.472 | 49.7664 | 59.7197 | 71.6636 | 85.9963 | 103.1956 | 123.8347 | 148.6017 | 148.6017
Free users (active) | 160 | 192 | 230.4 | 276.48 | 331.776 | 398.1312 | 477.7574 | 573.3089 | 687.9707 | 825.5649 | 990.6778 | 1188.8134 | 1188.8134
Revenue | 360 | 432 | 518.4 | 622.08 | 746.496 | 895.7952 | 1074.9542 | 1289.9451 | 1547.9341 | 1857.5209 | 2229.0251 | 2674.8301 | 14248.9808
Provider cost (paid) | 144 | 172.8 | 207.36 | 248.832 | 298.5984 | 358.3181 | 429.9817 | 515.978 | 619.1736 | 743.0084 | 891.61 | 1069.9321 | 5699.5923
Provider cost (free) | 64 | 76.8 | 92.16 | 110.592 | 132.7104 | 159.2525 | 191.103 | 229.3236 | 275.1883 | 330.2259 | 396.2711 | 475.5254 | 2533.1521
Stripe fees | 10.44 | 12.528 | 15.0336 | 18.0403 | 21.6484 | 25.9781 | 31.1737 | 37.4084 | 44.8901 | 53.8681 | 64.6417 | 77.5701 | 413.2204
Fixed infra | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 960
Gross profit | 61.56 | 89.872 | 123.8464 | 164.6157 | 213.5388 | 272.2466 | 342.6959 | 427.2351 | 528.6821 | 650.4185 | 796.5022 | 971.8026 | 4643.0159
Margin % | 17.1% | 20.8% | 23.89% | 26.46% | 28.61% | 30.39% | 31.88% | 33.12% | 34.15% | 35.02% | 35.73% | 36.33% | 32.58%
Cumulative profit | 61.56 | 151.432 | 275.2784 | 439.8941 | 653.4329 | 925.6795 | 1268.3754 | 1695.6104 | 2224.2925 | 2874.711 | 3671.2132 | 4643.0159 | 4643.0159
Notes:
• Conservative — does not include marketing-led spike or enterprise contracts.
• Edit blue cells (B5:B13) to model aggressive (e.g. 35% growth) or stress (e.g. 50% provider cost) scenarios.
• Margin should improve as fixed costs amortize across larger user base.

## Risks
Risk register
Score = Likelihood × Impact (1-3 each, max 9)
# | Risk | Likelihood (1-3) | Impact (1-3) | Score | Mitigation
R1 | Provider price shock (HF/fal/Replicate raises) | 2 | 3 | 6 | Multi-provider router; recalibrate quarterly
R2 | Abuse / NSFW / CSAM generation | 3 | 3 | 9 | Content moderation pre-call; ban + log; report endpoint
R3 | Stripe fraud (test cards, chargebacks) | 2 | 2 | 4 | Stripe Radar; min topup $5; email verify
R4 | HF cold-start kills latency SLO | 3 | 2 | 6 | Fallback provider; pre-warm cron; 5s timeout → fail-over
R5 | Free quota abuse via multi-account | 3 | 2 | 6 | Email verify + device fingerprint + 1 quota/fp
R6 | Copyright dispute on generated output | 2 | 2 | 4 | TOS shifts liability to user; record provenance hash
R7 | GDPR / data deletion request | 2 | 3 | 6 | DELETE endpoint; 90-day log retention; account deletion flow
R8 | Vercel function timeout (300s) on long jobs | 3 | 2 | 6 | Async queue (QStash); webhook callback
R9 | API key leak (committed to git, etc.) | 2 | 3 | 6 | Show key once; rotate endpoint; secret scanning
R10 | Dependency on single auth (Firebase) lock-in | 2 | 2 | 4 | Abstract auth in lib/auth/; OSS migration path doc

## Quick Wins
Top 5 quick wins (this week)
Impact-ranked, doable in <1 day each
# | Action | Why now | Effort
1 | Rotate every secret + clean .env.example | Real keys are committed in git history | 1h
2 | Add Upstash rate limit 60 req/min/key | Single bot can blow HF cost | 2h
3 | Refactor huggingface.ts to provider interface | Unblocks adding Replicate / Together | 3h
4 | Start usageLogs collection (no billing yet) | Need data before pricing decisions | 2h
5 | httpOnly session cookie via /api/auth/session | Current cookie is JS-readable → XSS risk | 2h